## Master sheet
| Overland Training Hike |  | 6th Lewes HQ | 12th March
Checkpoint | Location | Map Reference | Picture | Staff | Activity | Checkpoint Open time | Miles from previous CP | Time Allowed | First team arrival | Last team departure
Start | 6th Lewes HQ | TQ 421 094 |  | Fred, Keith, Leanne, Chris |  |  | 0 | 0:00 | 8:30 | 9:00
1 | Swanborough Manor | TQ 401 077 |  | Trident ESU. Laura, Ben | Planning a scout camp | 8:41 | 2.07 | 0:41 | 9:11 | 10:17
2 | Swanborough Hill | TQ 390 068 |  | 1st HH. Graham, Mike | Pioneering (broom sticks) | 9:11 | 0.96 | 0:19 | 9:41 | 11:01
3 | Balsdean | TQ 377 050 |  | 5th HH. Louise, Helen | Cities in Africa & S. America | 9:55 | 1.7 | 0:34 | 10:25 | 12:07
Finish | Woodingdean | TQ 356 063 |  | Keith, Fred, Chris |  | 10:49 | 2.21 | 0:44 | 11:19 | 13:28

## Joining Instructions
Joining Instructions
Column1 | Column2
District Event | Overland Training Hike
Start Location | 6th Lewes HQ
Finish Location | Woodingdean
Finish - Grid Reference | TQ 356 063
Finish - What3words | https://w3w.co/flattery.outwards.really
Parent drop off time | 0:00
Earliest estimated finish time | 11:19
Latest estimated Finish time | 13:28
Teams will be prompted to call for their lift home as they pass through the last checkpoint, which is approximately the following amount of minutes from the finish: | 0:44
Event Description | These hikes are a great opportunity to help prepare teams for the Overland Hiking competition and are open to everyone, including those that may be too young to enter the Overland itself. There are frequent checkpoints enroute for monitoring progress and where they will also tackle a fun checkpoint challenge.
Distance of route in miles | 6.94
One of the checkpoint challenges will be inspired by | Cities in Africa & S. America
Difficulty level of map reading; Easy/moderate/hard | Moderate - (Please could leaders arrange for an adult to escort teams with limited map reading experience)
In-Touch. Please follow In-Touch instruction provided to you by your Scout or Unit Leader. In an emergency, the nominated In-Touch person may contact the Leader in Charge on the District Mobile Telephone. | 07926925715
Kit List | Scout & Unit Leaders are responsible for checking completeness and suitability of all items listed on the kit list
Maps | OL11 Brighton & Hove
Please be notified that photographs may be taken of Scouts/teams by staff and posted on the 'closed' Mid Sussex Scout Hikes Facebook group | https://www.scouts.org.uk/volunteers/staying-safe-and-safeguarding/supporting-life-issues-and-young-people/digital-safeguarding/photography-video-and-audio-recording-at-scout-events/
Risk Assessment - Please see attached Risk Assessment | Here

## Kit List
Kit List
Personal Kit:
Waterproof lined rucksack
Waterproof coat with taped seams
Waterproof bottoms with taped seams
Waterproof hiking boots with ankle support
Long trousers
Long sleeved top
Fleece jumper
Warm hat
Gloves
Reflective items (on person and rucksack)
Spare fleece
Packed lunch and drink
Troop or unit neckerchief
Sleep bag, Roll mat Spare underwear & socks, Spare trousers, Spare long sleeve top Snacks, drink Troop or unit neckerchief Knife, Fork, Spoon, Plate, Bowl, Mug Torch.
Prohibited items:
Jeans
Shorts
Trainers
Team Equipment:
Comprehensive first aid kit (see Rule book for reference http://www.overlandhike.com/)
2x maps
2x map cases
2x compass
2x whistles
2x watches
2x survival bags
2x foil blankets
2x mobile phones with the what3words app downloaded (if able)
250g boiled sweets or chocolate
Paper & pencil

## Staff instructions & Site RA
Checkpoint Staff Instructions & Site Risk Assessment
Staff Instructions | Misc
Thank you for volunteering to support this hike. Your time is very much appreciated.
The Leader in Charge for this hike is: | Fred Thomas
The Leader in Charge can be contacted on the Districts' mobile phone. | 07926925715
The Leader in Charge may also be contacted on their personal phone (if happy to share) | '07553922144
Call the Leader in Charge if any problems arise during the hike.
Thoroughly read the Event Risk Assessment.
Be in position by the opening time stipulated for your location that's detailed on the master sheet. Call the Leader in Charge to advise that your checkpoint is now open. Keep your location open until you receive instruction from the Leader in Charge (or delegated authority) to close it.
If your location is adjacent to a road or has regular vehicle access, ensure staff moving around the checkpoint wear suitable High Visibility clothing.
Record arrival & departure times on control sheets and team log cards.
Run checkpoint challenges and record points on scoresheet: Checkpoint Challenges Print instructions of your challenge for the team to read. Where able, the challenge should be a practical “hands-on” task. Paper based quizzes are discouraged. 20 points are available for the challenge, apportion some points for teamwork. Do not give verbal assistance unless they are without a clue. Teams have a maximum of 10 minutes to complete the challenge, timed by the checkpoint staff, starting when you hand them the instruction sheet. Please stop them when their time is up. Checkpoint staff may need to be able to run their incident for a minimum of 2x teams simultaneously. See the Master Sheet for details of the challenge that has been assigned to your checkpoint.
Prior to the hike, email the Leader in Charge a copy of your Risk Assessment for risks associated with performing your checkpoint challenge.
Be contactable by phone (and provide a contact number for your location to the Leader in Charge).
First Aid: Carry out a very brief welfare check on each team. This means a visual check as the team’s approach, looking for signs of fatigue or injury, e.g. limping, blisters, sprains, hypothermia, dehydration etc. Ask each team: 1. about the welfare of each member. 2. to confirm that each team member wants to continue. If staff have any doubt about a team’s condition, they should contact the Leader in Charge and perform or request a First Aid assessment. Prompt the team to use their own emergency equipment/provisions as required. You are requested to have an adequate first aid kit and blankets available.
Check teams are wearing waterproofs if it's raining. Check shoelaces are tied.
Check Teams Hi-Vis is still visible i.e. they've not covered it up with coats.
If a team or individual withdraws from the hike, contact the Leader in Charge who will arrange collection.
Clearly display the next 'walk to' grid reference. Validate next checkpoint is correctly plotted and the intended route is understood by teams. Ensure Scouts leave in the correct direction. | "Walk to" grid ref'!A1
Do not leave checkpoints unattended for any reason before you have been officially closed down.
Each location will receive a checkpoint pack. Please note that, on some occasions, this maybe a soft copy for checkpoint staff to print as required. The hard copies of the checkpoint packs i.e. timings and score sheet will be collected by the Leader in Charge or delegated authority when your checkpoint is closed.
You will only be closed down when the last team reaches the next checkpoint.
Checkpoint Equipment: • Full first aid kit • Drinking water for teams • Stopwatch/timer/watch for timing the challenge. • Materials/equipment for your challenge
Location Specific Information
Start. 6th Lewes Scout HQ Description: Scout Hut, Ham Ln, Lewes BN7 3PS. Landowner: 6th Lewes (Fred is the lead contact for booking). Hazards: See separate attachment for Scout Hut RA. Comments: Start: Check team details are correct with attendees. Record 2x contact phone numbers for each team and check that these phones have ringers turned on to max volume. Brief teams to use the emergency number on the log card if they get into difficulty. Validate that teams are aware of correct route. Issue log card. | https://w3w.co/scripted.assure.gives
Start, photo.
Checkpoint 1 Name: Swanborough Manor Description: Roadside, road crossing. Landowner: Local authority. Hazards: Traffic on road, limited sighting of southbound traffic. Persons & property at risk: All participants. Risk controls in place: 50mph speed limit. Action to mitigate risk: Staff and teams to wear Hi-Viz. Staff will supervise teams when crossing the road. Important – wait for a gap in the traffic, do not attempt to stop the traffic. Comments: Staff must intercept teams before they cross. 4x4 team to put out caution walkerws crossing signs. Permission granted from Rhino Asphalt to park outside their offices (they're based on Swanborough Farm). Validate that teams have marked the next checkpoint correctly on their map and will follow the intended route. Sign team log cards. Please see picture below. | https://w3w.co/alarm.wicked.than
Checkpoint 1 photo
Checkpoint 2. Swanborough Hill. Description: Farm track, end of concrete road. Landowner: Hazards: Slow moving farm traffic. Persons & property at Risk: All participants. Risk Controls in place: Nil. Actions to mitigate risk: Staff and participants must wear hi-vis. Comments: Validate that teams have marked the next checkpoint correctly on their map and will follow the intended route. See photo of checkpoint 2 below. | https://w3w.co/spring.frames.trash
Checkpoint 2 photo and route across the open access land.
Checkpoint 3 Balsdean. Description: Farm track by path intersection. Landowner: Hazards: Slow farm traffic. Risk controls in place: Nil Comments: Muster teams safely away from traffic. Instruct teams to call their lift home to advise that they are approximately 30 minutes from the finish. Validate that teams have marked the next checkpoint correctly on their map and will follow the intended route. See photo of checkpoint 3 below. | https://w3w.co/fuzz.retraced.proofread
Checkpoint 3 photo.
Finish. Woodingdean, B2123. Description: Public Car Park. Landowner: Local Authority. Hazards: Traffic. Persons & property at risk: All participants. Risk controls in place: Nil. Action to mitigate risk: Staff and Teams to wear Hi-Vis. Safely muster teams away from the roadside. Comments:Collect log card. Check all team members are collected together (do not be left 1:1 with a scout). | https://w3w.co/flattery.outwards.really
Finish, photo.

## Event RA
Event Risk Assessment for Mid Sussex District Training Hikes
Person doing this RA | Date of RA | Date of Next Review | Date of Event
Chris Searle | 2022-12-20 | 2023-12-20 | 12th March
What hazard have you identified? What are the risks from it? | Who is at risk? | How are the risks already controlled? What extra controls are needed? | What has changed that needs to be thought about and controlled?
Risk of incidents consequent of insufficient organisation and planning | All participants | Organisers have produced a safety plan and a lines of communication flow chart. Key roles include: leader in charge, lead first aid, search & rescue and checkpoint staff.
Risk of incident or injury consequent of insufficient preparation for the terrain. | All participants | Organisers have checked and confirmed that the route is defined as (POR) Rule 9.28 Terrain Zero.
Risk of incident consequent of poor communications | All participants | Organisers to comply with the In Touch (POR) rule 9.3 OSM will collect contact details of parents, leaders and support staff. Hikers will provide a mobile telephone number for their team. The Leader in Charge will carry the District mobile telephone, the number will be shared with all parties.
Risk of an inadequate response to serious accident, injury or incident | All participants | Organisers to follow Purple Card procedure as required, to include escalation to 999 services as necessary.
Risk of inadequate adult supervision | All participants | Organisers to comply with the rules for adult to young person ratios
Risk of accident or injury when using your own car | All Drivers | All drivers of personal vehicles to read and comply with the ‘Using your own car for Scouting activities’ document.
Risk of unauthorised photographs being taken | All participants | Joining instructions will include a notification to parents that photographs may be taken of the Scouts and shared on the 'closed' Mid Sussex Scout Hikes Facebook page, in accordance with the legitimate interest section of the policy for 'photography, video and audio recording at Scout events.'
Lack of diversity and inclusion | All participants | The event is open and accessible to all members of the Scout and Explorer Sections.
Risk of teams being unsuitably equipped. | All participants | The Scout and Unit Leaders of teams are responsible for ensuring that participants carry a minimum of all items that are detailed on the Kit List
Risk of inexperience | All participants | Leaders must arrange adult supervision for teams that lack the experience and competence to complete the hike unsupervised. Teams hiking without an adult must be competent to navigate footpaths and bridleways using map and compass and can do so in limited visibility i.e. fog, mist and darkness.
Route Planning and Navigation | All participants | The route predominately follows footpaths and bridleways. At the start and at each checkpoint, teams will be advised of the grid reference for the next checkpoint that they will be walking to. Checkpoint staff will check with the team that they have plotted and will follow the intended route prior to departure.
Risk of Losing a Team/Individual. | All participants | Use of GPS Tracker was considered but is unviable due to a lack of funds. Inexperienced teams will be escorted or shadowed by an adult. All teams to have good knowledge & experience using Ordnance Survey Grid References. A minimum of two mobile phones to be carried by the team for emergency use. Leader in Charge will have a copy of these phone numbers. Teams are requested (if able) to download the what3words app onto their phones and be familiar with its use. Frequent checkpoints to be positioned along the route to monitor and record team progress. Teams to have the emergency telephone number written on their route card. Leaders to ensure that team members are trained upon the procedure for calling the emergency services. Support staff include a Search and rescue team. Organisers to produce a Safety & Emergency Plan and follow the plan as required. Leader in Charge to record all search and rescue activity on a written log. Participants to wear Hi-Vis Leaders to train teams how to use all of their emergency equipment prior to the hike e.g., 6 short sharp blasts of whistle repeated every minute etc. Teammates must hike closely bunched together. If anyone gets separated, then the team should stop and immediately call the Leader in Charge.
Risk of Injury - First Aid | All participants | In any First Aid situation the fellow team members should instruct the individual to carry out any treatment themselves, if practical. If not practical the First Aider (Team member or Leader) should wear surgical gloves while carrying out first aid. Each team to carry a first aid kit including all first aid items listed within Overland rulebook. Each Search & Rescue vehicle must carry a comprehensive first aid kit. Any injuries must be phoned through to the Leader in Charge. Leader in Charge may deploy the Lead First Aider to tend to the casualty as required. Checkpoint staff to complete a quick welfare check as teams pass through, to include checking for anybody that’s limping, in obvious pain, suffering from exposure etc. 111 can be called for advice regarding treatments of a minor nature. Purple Card procedure will be followed in the event of serious accident or injury, to include calling for 999 services as required.
Risk of Hypothermia, dehydration, Exhaustion (Fatigue), Burns/blisters/sprains/ insect bites | All participants | Dehydration - All participants will carry a personal water supply that must be replenished at each checkpoint. Hypothermia – The Equipment List and rules mandates the wearing of appropriate clothing, the carrying (or wearing) of wet weather clothing & spare dry clothing, the carrying of 2x bivi or survival bag. Scout and Unit Leaders are responsible for checking or suitability and completeness of clothing and all other items on the kit list. Leader in Charge to monitor weather conditions. Exhaustion – Pace to be set by the slowest member of the team. Teams to carry lunch and snacks. Insect Bites, Burns, Blisters, Sprains – First aid to be administered as required. Teams to phone Leader in Charge to request medical assistance for all of the above as required, or report to checkpoint staff if becoming symptomatic at a checkpoint. Team members must be trained in recognising the signs of distress in other team members. Checkpoint staff to perform a welfare check at checkpoints. Leaders to familiarise and train their teams to use the first aid kit that they carry with them on the hike as required.
Terrain. Risk of slips, trips and falls due to ground conditions such as slopes, obstacles, mud, uneven surface, frost, ice & snow etc) | All participants | Equipment list mandates the use of appropriate hiking footwear for all participants. Participants will include experienced hikers who will train inexperienced hikers to observe all normal precautions. The event routing will be over established public rights of way. Teams must not intentionally deviate.
Risk of Adverse Weather. | All participants | Organisers will monitor weather reports and actual conditions on the day. Teams must wear appropriate waterproof boots and clothing for the prevailing and forecast conditions. Scout & Unit Leaders to brief their teams of the need to monitor the weather throughout the hike and wear/change into appropriate clothing from their kit. The Leader in Charge will stop the event if weather conditions are unsafe.
The risk of traffic danger. | All participants | Staff to place “caution walkers crossing” signs to warn traffic on approach to busy road crossings. Teams to use the highway code when walking and crossing minor roads. The wearing of Hi-Vis is mandatory at all times. Inexperienced teams will be escorted by an adult who will supervise crossings and compliance to the highway code.
Risk of teams not following the Country Code | All participants | Leaders to train all participants the Countryside Code as part of their eligibility to participate.
Risk of Drowning | All participants | There are no rivers on this route. Teams must remain a safe distance from the waters edge when walking past ponds and cross streams using the public rights of way.
Risk of incident or injury at checkpoint and service area locations | All participants | Organisers have produced site specific Risk Assessments for each checkpoint location. This RA will be included in the checkpoint packs and issued to check staff accordingly. Checkpoint staff must create a Risk Assessment for their checkpoint activity which must be submitted for approval to the Leader in Charge prior to the hike.
Risk of mobile telephone coverage blackspots or outages adversely affecting incident management and tracking of teams. | All participants | Use of mobile phone technology is used in support of traditional methods of tracking teams, such as recording team arrival and departure times at checkpoints.
Risk of incident or injury at future Scouting events consequent from failing to report a near miss. | All participants | To help ensure that an incident won’t happen again to someone else, leading to injury or damage. The Leader in Charge will log any ‘near miss’ potentially unsafe incidents with UK Headquarters.

## CP Score sheet
Mid Sussex District Scouts
Checkpoint Score Sheet |  |  | Checkpoint | Start | 6th Lewes HQ
Time Taken | Hike Points | Team Number | Arrival Time | Departure Time | Hike Points2 | Incident Points | Signed
0:00 | 20 | 1
0:01 | 19 | 2
0:02 | 18 | 3
0:03 | 17 | 4
0:04 | 16 | 5
0:05 | 15 | 6
0:06 | 14 | 7
0:07 | 13 | 8
0:08 | 12 | 9
0:09 | 11 | 10
0:10 | 10 | 11
0:11 | 9 | 12
0:12 | 8 | 13
0:13 | 7 | 14
0:14 | 6 | 15
0:15 | 5 | 16
0:16 | 4 | 17
0:17 | 3 | 18
0:18 | 2 | 19
0:19 | 1 | 20
Mid Sussex District Scouts
Checkpoint Score Sheet |  |  | Checkpoint | 1 | Swanborough Manor
Time Taken | Hike Points | Team Number | Arrival Time | Departure Time | Hike Points2 | Incident Points | Signed
0:41 | 20 | 1
0:42 | 19 | 2
0:43 | 18 | 3
0:44 | 17 | 4
0:45 | 16 | 5
0:46 | 15 | 6
0:47 | 14 | 7
0:48 | 13 | 8
0:49 | 12 | 9
0:50 | 11 | 10
0:51 | 10 | 11
0:52 | 9 | 12
0:53 | 8 | 13
0:54 | 7 | 14
0:55 | 6 | 15
0:56 | 5 | 16
0:57 | 4 | 17
0:58 | 3 | 18
0:59 | 2 | 19
1:00 | 1 | 20
Mid Sussex District Scouts
Checkpoint Score Sheet |  |  | Checkpoint | 2 | Swanborough Hill
Time Taken | Hike Points | Team Number | Arrival Time | Departure Time | Hike Points2 | Incident Points | Signed
0:19 | 20 | 1
0:20 | 19 | 2
0:21 | 18 | 3
0:22 | 17 | 4
0:23 | 16 | 5
0:24 | 15 | 6
0:25 | 14 | 7
0:26 | 13 | 8
0:27 | 12 | 9
0:28 | 11 | 10
0:29 | 10 | 11
0:30 | 9 | 12
0:31 | 8 | 13
0:32 | 7 | 14
0:33 | 6 | 15
0:34 | 5 | 16
0:35 | 4 | 17
0:36 | 3 | 18
0:37 | 2 | 19
0:38 | 1 | 20
Mid Sussex District Scouts
Checkpoint Score Sheet |  |  | Checkpoint | 3 | Balsdean
Time Taken | Hike Points | Team Number | Arrival Time | Departure Time | Hike Points2 | Incident Points | Signed
0:34 | 20 | 1
0:35 | 19 | 2
0:36 | 18 | 3
0:37 | 17 | 4
0:38 | 16 | 5
0:39 | 15 | 6
0:40 | 14 | 7
0:41 | 13 | 8
0:42 | 12 | 9
0:43 | 11 | 10
0:44 | 10 | 11
0:45 | 9 | 12
0:46 | 8 | 13
0:47 | 7 | 14
0:48 | 6 | 15
0:49 | 5 | 16
0:50 | 4 | 17
0:51 | 3 | 18
0:52 | 2 | 19
0:53 | 1 | 20
Mid Sussex District Scouts
Checkpoint Score Sheet |  |  | Checkpoint | Finish | Woodingdean
Time Taken | Hike Points | Team Number | Arrival Time | Departure Time | Hike Points2 | Incident Points | Signed
0:44 | 20 | 1
0:45 | 19 | 2
0:46 | 18 | 3
0:47 | 17 | 4
0:48 | 16 | 5
0:49 | 15 | 6
0:50 | 14 | 7
0:51 | 13 | 8
0:52 | 12 | 9
0:53 | 11 | 10
0:54 | 10 | 11
0:55 | 9 | 12
0:56 | 8 | 13
0:57 | 7 | 14
0:58 | 6 | 15
0:59 | 5 | 16
1:00 | 4 | 17
1:01 | 3 | 18
1:02 | 2 | 19
1:03 | 1 | 20

## "Walk to" grid ref
12th March
Walk To Grid Reference:
TQ 401 077
Start to CP1
12th March
Walk To Grid Reference:
TQ 390 068
CP1 to CP2
12th March
Walk To Grid Reference:
TQ 377 050
CP2 to CP3
12th March
Walk To Grid Reference:
TQ 356 063
CP3 to Finish

## Safety plan
Overland Training Hikes Safety Plan
1. Search and Rescue will be coordinated by the Leader in Charge.
2. Search and Rescue could be conducted by any of, or by combination of, the following: Search & Rescue Team(S). Other teams in close proximity. Staff at checkpoints that have previously been made aware that they may be called upon to assist. Emergency Services (purple card procedure).
3. All search and rescues to be logged and recorded.
4. When a team is considered overdue they are to be contacted on their mobile phone by the Leader in Charge or delegated authority
4a. If a team is contacted and lost, a search and rescue will be started. This will be based on:
The information the team can give.
Teams are also requested to download the GPS location app what3words https://what3words.com/products/what3words-app.
The checkpoint that the team were last known to depart.
4b. If a team know where they are and are being withdrawn then the Leader in Charge will arrange recovery of the team.
4c. If no contact is made with the team by mobile phone then a search will be initiated.
5. The Leader in Charge will nominate a rendezvous point for search teams based on the information from the teams last known position. Staff will have access to maps of the route with known vehicle access and egress points.
6. The Leader in Charge will dispatch search teams to the position.
7. Should the team not be at the last known position, then other areas will be searched as directed by the Leader in Charge.
8. A log is to be kept of areas searched and at what time.
9. If an incident requires first aid, the Lead First Aider will be called to a location decided by the Leader in Charge. Until help arrives, staff may prompt the team to use appropriate emergency equipment that the team is mandated to carry e.g. survival bag, first aid kit, emergency food/drink etc.
10. Search and Rescue team to drive on any roads that the team may be walking on, this is to be logged.
11. Leader in Charge to instigate purple card procedure if required, to include escalation to 999 services as necessary.
12. Search will continue until the team is found.
13. If the entire event becomes too unsafe to continue e.g. due to extreme weather conditions, then the event will be closed by stopping teams at checkpoints, whereby their staff and In-Touch contacts will organise their collection and departure from the event. Team departures will be recorded by checkpoint staff and communicated back to the Leader in Charge.

## Comms
Major incident or injury
(Purple Card Emergency)
District Commissioner or Designate (Purple Card Emergency)
Lines of Communication
In the Field
Remote
Key
Minor incident or injury
Incident management
In-Touch Contact
Leader In Charge
Parents
Search & Rescue
Checkpoint Staff
Lead First Aider
Teams
Staff communication

## Contacts
Contacts
Role | Name | Phone Number
Leader in Charge | Fred Thomas | '07553922144
Leader in Charge | District mobile number | 07926925715
Purple Card Contact | Mark Scholfield | 07921020154
Lead First Aider | 0 | 0
Nights Away Permit Holder | 0 | 0
Search & Rescue 1 | Chris Searle | '07899934036
Search & Rescue 2 | 0 | 0
Search & Rescue 3 | 0 | 0
Search & Rescue 4 | 0 | 0
Start | Fred, Keith, Leanne, Chris | 0
CP1 | Trident ESU. Laura, Ben | 0
CP2 | 1st HH. Graham, Mike | 0
CP3 | 5th HH. Louise, Helen | 0
CP4 | 0 | 0
CP5 | 0 | 0
CP6 | 0 | 0
CP7 | 0 | 0
Finish | Keith, Fred, Chris | 0

## Search & Rescue Log
Search & Rescue Log
Team number |  |  |  | Last known location
Time at location |  |  |  | Walking to
Search Log Number | Searched by | Start Location | Grid Ref | Finish Location | Grid Ref2 | Start Time | Finish Time | Direction
Comments:

## Log Card
Overland Training Hike |  |  | Team Number
Checkpoint | Arrival Time | Departure Time | Hike Points | Signature
Start
CP1
CP2
CP3
CP4
CP5
CP6
CP7
Finish
Total Hike Points=
Emergency Contact Number |  | 07926925715
Overland Training Hike |  |  | Team Number
Checkpoint | Arrival Time | Departure Time | Hike Points | Signature
Start
CP1
CP2
CP3
CP4
CP5
CP6
CP7
Finish
Total Hike Points=
Emergency Contact Number |  | 07926925715
Log Card Overland Training Hike
|  |  | Emergency Contact Number | 07926925715
Log Card Overland Training Hike
|  |  | Emergency Contact Number | 07926925715

## Master Points
Enter values in yellow boxes
MASTER POINTS CONTROL SHEET
TROOP | Team Number | CP1 | CP2 | CP3 | CP4 | Hike Points | Total Points | Position
|  | 20 | 20 | 20 | 20 | 100 | 180 | Available points
| 1 | [5 empty] | 0 | 1
| 2 | [5 empty] | 0 | 1
| 3 | [5 empty] | 0 | 1
| 4 | [5 empty] | 0 | 1
| 5 | [5 empty] | 0 | 1
| 6 | [5 empty] | 0 | 1
| 7 | [5 empty] | 0 | 1
| 8 | [5 empty] | 0 | 1
| 9 | [5 empty] | 0 | 1
| 10 | [5 empty] | 0 | 1

## Data
Enter values in yellow boxes
|  |  |  | Speed (MPH) of team= |  | 3 | Estimated speed (MPH) of slower teams= |  | 2
Checkpoint | Location | Map Reference | Distance (miles) from previous checkpoint | Time allowed | First team arrival | First team departure | Estimated time for slowest team | Last team arrival | Last team departure
Start | 6th Lewes HQ | TQ 421 094 |  | 0:00 | 8:30 | 8:30 | 0:00 | 9:00 | 9:00
1 | Swanborough Manor | TQ 401 077 | 2.07 | 0:41 | 9:11 | 9:21 | 1:02 | 10:02 | 10:17
2 | Swanborough Hill | TQ 390 068 | 0.96 | 0:19 | 9:41 | 9:51 | 0:29 | 10:46 | 11:01
3 | Balsdean | TQ 377 050 | 1.7 | 0:34 | 10:25 | 10:35 | 0:51 | 11:52 | 12:07
Finish | Woodingdean | TQ 356 063 | 2.21 | 0:44 | 11:19 | 11:29 | 1:06 | 13:13 | 13:28
| Total Mileage | 6.94
| Date of hike= | 12th March
Map | OL11 Brighton & Hove
Role | Name | Number
Leader in Charge | Fred Thomas | '07553922144 | Type an apostrophy before entering your number
Leader in Charge | District mobile number | 07926925715
Purple Card Contact | Mark Scholfield | 07921020154
Lead First Aider
Nights Away Permit Holder
Search & Rescue 1 | Chris Searle | '07899934036
Search & Rescue 2
Search & Rescue 3
Search & Rescue 4
Start | Fred, Keith, Leanne, Chris
CP1 | Trident ESU. Laura, Ben
CP2 | 1st HH. Graham, Mike
CP3 | 5th HH. Louise, Helen
CP4
CP5
CP6
CP7
Finish | Keith, Fred, Chris